## Assumptions
TNPM Platform — Cost Estimate (Build-From-Scratch)
Currency: VND (blended Vietnam mid-tier rate, 2026)
Methodology: Bottom-up MM x Role rate. 1 MM = 22 ngày x 8h = 176 effective hours.
# | Role | Rate (VND/MM) | Seniority | Note
1 | Tech Lead / Solution Architect | 60000000 | 10+ yrs | Decision kiến trúc, code review, mentoring
2 | Senior Backend Engineer | 50000000 | 7-10 yrs | Java/Spring Boot 3.2 / Vert.x / Kafka / jOOQ
3 | Mid Backend Engineer | 35000000 | 3-5 yrs | Implement domain, test, code review junior
4 | Senior Frontend Engineer | 45000000 | 5+ yrs | React/TS, lead FE module, design system
5 | Mid Frontend Engineer | 30000000 | 2-4 yrs | Build page, integrate API, write test
6 | DevOps / Platform Engineer | 45000000 | 5+ yrs | K8s, Kafka/RabbitMQ, ES, Prometheus, CI/CD
7 | Security Engineer | 50000000 | 5+ yrs | Pentest, NHNN compliance, audit log design
8 | QA Lead / Test Architect | 35000000 | 5+ yrs | Test strategy, automation lead
9 | QA Engineer | 22000000 | 2-4 yrs | E2E, smoke, regression, manual UAT
10 | Project Manager | 40000000 | 5+ yrs | Schedule, stakeholder, risk, billing
11 | Business Analyst | 35000000 | 3-5 yrs | Refine spec, user story, UAT support
12 | UX/UI Designer | 35000000 | 3-5 yrs | Wireframe, design system, prototype
Global parameters
USD/VND exchange rate | 24500
Contingency % (Standard scenario) | 15%
Project Overhead % | 10%
Contingency % (Lean) | 10%
Contingency % (Safe) | 25%
Lean direct labor reduction % | 10%
Safe indirect cost increase % | 20%

## Effort_by_Module
Effort by Module — Man-Month per Role
Phase | Module / Service | BE Senior | BE Mid | FE Senior | FE Mid | QA Lead | QA Eng | Other (DevOps/Sec/TL) | Total MM | Module Cost (VND)
Phase 1 | iam-service (multi-tenant, RBAC, OAuth2/JWT) | 1.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 4 | 162500000
Phase 1 | portfolio-service (Portfolio>Project>Building>Floor>Space>Unit — 8 NEW) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 85000000
Phase 1 | customer-service (REUSE + extend property segment) | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 1.5 | 60000000
Phase 1 | contract-service P1 (service contract base) | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 102500000
Phase 1 | billing-service P1 (fee, rate, meter EVN bậc thang, invoice batch) | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 205000000
Phase 1 | payment-service P1 (cash, debt ledger, MSB/Timi base) | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 3.5 | 145000000
Phase 1 | operations-service P1 (Service Request, complaint ticket) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 85000000
Phase 1 | notification-service P1 (template SMS/Email) | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 1.5 | 60000000
Phase 1 | FE P1 (~12 page core: portfolio, customer, contract, billing, debt, SR, setting) | 0 | 0 | 2.5 | 5.5 | 0 | 0 | 0 | 8 | 277500000
Phase 1 | QA P1 (smoke + integration + E2E) | 0 | 0 | 0 | 0 | 1.5 | 4.5 | 0 | 6 | 151500000
Phase 2 | payment-service full (gateway VNPay/MoMo, auto-debit, webhook security) | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 3 | 127500000
Phase 2 | vendor-service (12 NEW: master, KPI, 3-way match, approval 4-step) | 3.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 8 | 332500000
Phase 2 | notification-service P2 (campaign manual + template engine full) | 0.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2 | 77500000
Phase 2 | report-service P2 (P&L per project, vendor list) | 0.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2 | 77500000
Phase 2 | FE P2 (~6 page vendor, invoice, KPI, gateway settings, partner) | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 6 | 210000000
Phase 2 | QA P2 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 4 | 101000000
Phase 3 | contract-service lease nâng cao (escalation, deposit, auto-renew) | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 3 | 127500000
Phase 3 | billing-service CAM allocation + Turnover Rent formula | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 170000000
Phase 3 | compliance-service (B2G kho bạc + audit log + tenant scan — 10 NEW) | 3.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 8 | 332500000
Phase 3 | operations-service Maintenance Plan + SLA escalation | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 85000000
Phase 3 | notification-service auto rule engine (12 NEW) | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 1.5 | 60000000
Phase 3 | FE P3 (~10 page: lease 4 tab, CAM, turnover, B2G, maintenance, audit log) | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 6 | 210000000
Phase 3 | QA P3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 4 | 101000000
Portal+Integration | Portal auth domain (separate IAM + magic link + OTP SMS) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 85000000
Portal+Integration | Owner Portal UI (CĐT read-only dashboard P&L) | 0 | 0 | 0.5 | 1.5 | 0 | 0 | 0 | 2 | 67500000
Portal+Integration | Vendor Portal UI (NCC submit invoice, approval status) | 0 | 0 | 0.5 | 1.5 | 0 | 0 | 0 | 2 | 67500000
Portal+Integration | Integration adapter MSB/Timi/VNPay/MoMo (4 adapter + HMAC + idempotency) | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 3.5 | 145000000
Portal+Integration | Portal QA + integration test | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 0 | 2 | 50500000
Cross-cutting | Tech Lead / Architect (toàn dự án) | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 310625000
Cross-cutting | DevOps / Platform (K8s, RabbitMQ/Kafka, ES, Prometheus, CI/CD) | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 266250000
Cross-cutting | Security Engineer (pentest, NHNN compliance, audit log) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 88750000
Cross-cutting | Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 310625000
Cross-cutting | Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 266250000
Cross-cutting | UX/UI Designer (design system extension TNPM) | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 177500000
Cross-cutting | Knowledge transfer + onboarding + ramp-up buffer | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 443750000
TỔNG | Direct Labor (toàn bộ effort) | 26 | 35 | 7.5 | 16.5 | 4 | 12 | 42 | 143 | 5625250000
Subtotal theo Phase
Phase 1 | [8 empty] | 36 | 1334000000
Phase 2 | [8 empty] | 25 | 926000000
Phase 3 | [8 empty] | 28.5 | 1086000000
Portal+Integration | [8 empty] | 11.5 | 415500000
Cross-cutting | [8 empty] | 42 | 1863750000

## Indirect_Costs
Indirect Costs — Infra, Tools, 3rd-party
# | Hạng mục | Giá trị (VND) | Ghi chú
1 | Cloud infra (dev + staging + prod) 18 tháng | 600000000 | K8s managed cluster, DB (PostgreSQL HA), Redis, ES cluster 3-node, RabbitMQ, S3, monitoring stack
2 | Tools & License | 100000000 | Jira/Confluence team, Figma Pro, GitLab Premium, Snyk + SonarQube
3 | 3rd-party — Pentest 1 round | 80000000 | External pentest firm, full report + retest
4 | 3rd-party — MSB Pay onboarding & cert | 50000000 | Merchant onboarding fee + UAT cost
5 | 3rd-party — Timi API access | 30000000 | Setup + integration fee
6 | 3rd-party — sInvoice license | 40000000 | Hoá đơn điện tử license + integration
TỔNG | Indirect Cost Subtotal | 900000000

## Summary
TNPM Platform — Cost Summary (Build-From-Scratch)
Scope: Web Admin + 12 microservice BE (Phase 1-3) + Owner/Vendor Portal + Integration MSB/Timi/VNPay/MoMo
Hạng mục | Lean (~6.6tỷ) | Standard (~8.1tỷ) | Safe (~9.0tỷ) | Ghi chú
Direct Labor | 5062725000 | 5625250000 | 5625250000 | Sum effort × rate per role
Indirect Cost | 900000000 | 900000000 | 1080000000 | Infra + Tools + 3rd-party
Subtotal (DL + IC) | 5962725000 | 6525250000 | 6705250000
Contingency | 596272500 | 978787500 | 1676312500 | Buffer rủi ro
Project Overhead | 596272500 | 652525000 | 670525000 | PM admin, license amortization
TỔNG VND | 7155270000 | 8156562500 | 9052087500
TỔNG USD (tham chiếu) | 292051.8367 | 332920.9184 | 369472.9592 | @ 1 USD = 24,500 VND
Effort Summary
Bucket | MM
Phase 1 (BE + FE + QA) | 36
Phase 2 (BE + FE + QA) | 25
Phase 3 (BE + FE + QA) | 28.5
Portal + Integration | 11.5
Cross-cutting (TL/PM/BA/UX/DevOps/Sec) | 42
TỔNG MM | 143
Khuyến nghị
1. Dùng Standard ~8.1 tỷ VND làm cost basis chào TNTech để align internal.
2. Lean ~6.6 tỷ chỉ khả thi khi Reborn reuse retail >= 60% + team senior đa năng.
3. Safe ~9.0 tỷ khi có CĐT lớn cần SSO/SAML, data migration, NHNN compliance scope full.
4. Out-of-scope (tính riêng): Mobile cư dân +1.5tỷ, AI debt +800M, POS integration, Data migration, Hotline call center, On-premise deploy.
5. Cost này KHÔNG phải pricing cho TNPM — pricing = cost × (1 + margin 30-50%) tuỳ engagement model (xem 07-business-case/).
6. Annual maintenance fee (sau go-live) = 15-20% cost build/năm, tính riêng.

## Scenario_Comparison
Scenario Comparison & Sensitivity
Để TNTech chỉnh tham số trực tiếp và xem tác động lên TỔNG.
Scenario | Direct Labor (VND) | Indirect (VND) | Contingency % | Overhead % | TỔNG VND
Lean | 5062725000 | 900000000 | 10% | 10% | 7155270000
Standard | 5625250000 | 900000000 | 15% | 10% | 8156562500
Safe | 5625250000 | 1080000000 | 25% | 10% | 9052087500
Out-of-scope add-ons (tính riêng nếu TNPM yêu cầu)
Add-on | Ước tính VND | MM | Khi nào cần
Mobile cư dân Timi-like (React Native) | 1500000000 | 22 | Khi TNPM không dùng app Timi sẵn có
AI phân tích công nợ | 800000000 | 12 | Phase 4 — cần data >= 6 tháng
POS Integration cho TTTM tenant | 400000000 | 6 | Khi tenant TTTM lớn yêu cầu turnover auto
Data migration từ hệ thống cũ TNPM | 600000000 | 9 | Tuỳ độ phức tạp data source
Hotline call center integration | 300000000 | 4 | Cần đối tác viễn thông + thiết bị
On-premise deployment package | 500000000 | 7 | Khi TNPM yêu cầu on-prem thay vì cloud
SSO/SAML cho CĐT lớn (per CĐT) | 250000000 | 3.5 | Vinhomes, AEON, etc.

## OPEX_Segments
OPEX — 4 segment scale TNPM (chưa khoá quy mô)
Chọn segment phù hợp khi TNPM xác nhận quy mô. TNPM ROX Key hiện tại likely là L.
Dimension | S — Pilot | M — Mid-scale | L — Large (TNPM likely) | XL — Enterprise | Note
# Projects (dự án) | 1-3 | 4-15 | 15-50 | 50+ | Multi-tenant project
# Units / Space | ≤ 500 | 500-3,000 | 3,000-15,000 | 15,000+ | Đơn vị nhà/mặt bằng
# Customers (cư dân + B2B) | ≤ 2,000 | 2k-15k | 15k-60k | 60k+ | Active customers
Invoices / tháng | ~1,000 | 3k-15k | 20k-60k | 80k+ | Hoá đơn phát hành định kỳ
Payment tx / tháng | ~700 | 2k-10k | 15k-45k | 60k+ | Giao dịch thanh toán
Concurrent users (peak) | ~50 | 100-300 | 400-1,000 | 1,500+ | Cao điểm ngày mồng 1-8
Mô tả thực tế | Pilot 1-2 chung cư | TNPM năm đầu — VP + KCN nhỏ + chung cư | Toàn portfolio ROX Key — 7 loại property | Mở white-label cho 3rd-party CĐT (Vinhomes, Sun Group...)
Volume estimates / tháng (input cho Pass-through sheet)
Volume metric | S | M | L | XL | Đơn giá tham chiếu
Invoices / tháng | 1000 | 9000 | 40000 | 100000 | — (đầu vào cho SMS/Email/Zalo/sInvoice)
Payment transactions / tháng | 700 | 6000 | 35000 | 80000 | MSB ~5,000-10,000đ/tx, VNPay/MoMo ~3,000đ/tx
SMS / tháng (5x invoice) | 5000 | 45000 | 200000 | 500000 | Viettel/VNPT ~600đ/SMS, volume contract ~400đ
Email / tháng (5x invoice) | 5000 | 45000 | 200000 | 500000 | SendGrid/Mailgun ~100đ/email
Zalo OA / tháng (1x invoice) | 1000 | 9000 | 40000 | 100000 | ~500đ/notification
sInvoice (HĐ điện tử) / tháng | 1000 | 9000 | 40000 | 100000 | ~1,000-2,000đ/HĐ tuỳ provider

## OPEX_PlatOps
Platform Operating Cost (PlatOps) per segment — VND/tháng
9 component / segment. Đơn vị: triệu VND/tháng. Reborn/operator gánh — không phụ thuộc volume tx.
# | Component | S | M | L | XL
1 | Cloud Infrastructure (K8s, DB HA, Redis, ES, RabbitMQ, S3) | 25000000 | 80000000 | 250000000 | 700000000
2 | Licenses & Tools (monitoring, security scan, Jira/Figma) | 8000000 | 15000000 | 30000000 | 60000000
3 | DevOps / SRE team (FTE × loaded rate) | 22500000 | 45000000 | 100000000 | 220000000
4 | Application Support L1/L2/L3 | 15000000 | 35000000 | 90000000 | 220000000
5 | Annual Maintenance & Evolution (15-20% cost build/12) | 100000000 | 110000000 | 130000000 | 160000000
6 | Backup & DR (cross-AZ, 30d retention, RTO 4h) | 5000000 | 15000000 | 45000000 | 120000000
7 | Compliance & Security Audit (pentest + NHNN audit /12) | 10000000 | 15000000 | 25000000 | 40000000
8 | Training & Documentation | 3000000 | 8000000 | 15000000 | 30000000
9 | Vendor management buffer (cloud overages, ES upgrade) | 10000000 | 20000000 | 50000000 | 100000000
| TỔNG PlatOps / tháng | 198500000 | 343000000 | 735000000 | 1650000000
| TỔNG PlatOps / năm | 2382000000 | 4116000000 | 8820000000 | 19800000000
| Ratio PlatOps/năm vs CAPEX (Standard 8.16 tỷ) | 29.2% | 50.46% | 108.1% | 242.7%

## OPEX_PassThrough
Pass-through Usage Cost per segment — VND/tháng
Volume × đơn giá. TNPM trực tiếp gánh — không phụ thuộc engagement model. Khuyến nghị TNPM thu lại từ KH cuối.
# | Component | S | M | L | XL
1 | MSB / VNPay transaction fee (blended 5,000đ/tx) | 3500000 | 30000000 | 175000000 | 400000000
2 | SMS OTP + nhắc nợ (600đ/SMS) | 3000000 | 27000000 | 120000000 | 300000000
3 | Email (100đ/email) | 500000 | 4500000 | 20000000 | 50000000
4 | Zalo OA (500đ/noti) | 500000 | 4500000 | 20000000 | 50000000
5 | sInvoice (1,000đ/HĐ) | 1000000 | 9000000 | 40000000 | 100000000
| TỔNG Pass-through / tháng | 8500000 | 75000000 | 375000000 | 900000000
| TỔNG Pass-through / năm | 102000000 | 900000000 | 4500000000 | 10800000000

## OPEX_Summary
OPEX Summary — Annual + TCO 3 năm
Tổng hợp PlatOps + Pass-through và Total Cost of Ownership 3 năm cho từng segment.
Hạng mục | S — Pilot | M — Mid | L — Large | XL — Enterprise | Note
PlatOps / năm | 2382000000 | 4116000000 | 8820000000 | 19800000000 | Reborn/operator gánh
Pass-through / năm | 102000000 | 900000000 | 4500000000 | 10800000000 | TNPM gánh, scale volume
TỔNG OPEX / năm | 2484000000 | 5016000000 | 13320000000 | 30600000000
TCO 3 năm — TNPM (Reborn managed SaaS, margin PlatOps 35%)
Hạng mục | S | M | L | XL | Note
Year 1 — CAPEX chào TNPM (Standard + 35% margin) | 11011359375 | 11011359375 | 11011359375 | 11011359375 | 1 lần, có Lean/Safe option
Year 1-2-3 — PlatOps × 1.35 margin / năm | 3215700000 | 5556600000 | 11907000000 | 26730000000 | SaaS subscription bill TNPM
Year 1-2-3 — Pass-through at-cost / năm | 102000000 | 900000000 | 4500000000 | 10800000000 | Bill at-cost, transparent
Year 1 total TNPM trả | 14329059375 | 17467959375 | 27418359375 | 48541359375 | CAPEX + 1 năm OPEX
Year 2 total | 3317700000 | 6456600000 | 16407000000 | 37530000000 | Subscription only
Year 3 total | 3317700000 | 6456600000 | 16407000000 | 37530000000 | Subscription only
TCO 3 năm | 20964459375 | 30381159375 | 60232359375 | 123601359375 | Số TNPM cần budget
Khuyến nghị OPEX
1. TNPM ROX Key hiện tại likely thuộc segment L — confirm với TNPM trong buổi discovery để chốt.
2. Pass-through cost (MSB tx, SMS, sInvoice) khuyến nghị TNPM thu lại từ KH cuối — không gánh trên P&L vận hành.
3. PlatOps L = 8.82 tỷ/năm ≈ 108% CAPEX (8.16 tỷ) — chuẩn industry SaaS B2B năm 1-2, sẽ giảm xuống ~60% năm 3+ qua optimization.
4. SaaS managed model: Reborn margin PlatOps 25-40% (chốt 35% trong sheet này). Pass-through bill at-cost transparent.
5. Hybrid: Reborn host 12-18 tháng đầu, TNPM có option migrate on-premise sau — minimize risk 2 bên.
6. Industry benchmark TCO 3 năm: Yardi 50-80 tỷ, MRI 60-100 tỷ. Local custom + Reborn managed nên rơi 50-65 tỷ (L segment) → competitive.